## Sheet1
Sub-Task ID | Sub-Task Name | RASCI | Start Date | End Date | Duration (days) | Effort (days) | Dependencies | Critical Path | Deliverable | Risks/Issues/Assumptions/Dependencies
1.1 | Identify & Confirm Sponsor and Steering Committee Members | R: Project Manager; A: Sponsor; S: Product Manager; C: CTO, CRO, ESG Lead, CIOs; I: All Stakeholders | 2025-06-10 | 2025-06-12 | 3 | 3 |  | Yes | Finalized list of sponsor + steering committee | Assumes sponsor availability; potential scheduling conflicts
1.2 | Schedule Individual Kickoff Meetings with Each Stakeholder Group | R: Project Manager; A: Sponsor; S: Product Manager; C: –; I: All Stakeholders | 2025-06-13 | 2025-06-17 | 5 | 5 | 1.1 | Yes | Calendar invites + meeting agendas | Tight stakeholder schedules; assumption that all N-1 weeks are free
1.3 | Conduct Kickoff Workshop with Investment Leadership (CIOs & Chief Strategist) | R: Product Manager; A: CIOs; S: Project Manager; C: AI/ML Lead, Risk Analyst, ESG Lead; I: Investment Team | 2025-06-18 | 2025-06-20 | 3 | 3 | 1.2 | Yes | Workshop minutes + high-level needs capture | Aligning on “what long-term alpha means” may take longer than planned
1.4 | Conduct Session with Risk Committee & CRO to Capture Risk/Compliance Concerns | R: Risk Analyst; A: CRO; S: Project Manager; C: AI/ML Lead, Compliance; I: Steering Committee | 2025-06-21 | 2025-06-23 | 3 | 3 | 1.2 | Yes | Risk-concerns document (model risk, data privacy) | Some concerns (e.g., use of unverified alt data) may require follow-up research
1.5 | Conduct Workshop with ESG/Sustainability Team | R: ESG Lead; A: ESG Head; S: Product Manager; C: AI/ML Lead, Risk Analyst; I: Steering Committee | 2025-06-24 | 2025-06-26 | 3 | 3 | 1.2 | Yes | ESG requirements write-up (metrics, scoring needs) | Possible overlap with Risk concerns (need to reconcile)
1.6 | Hold Sessions with Front-line Investment Teams (Equity, Fixed Income, Private Equity) | R: Product Manager; A: Portfolio Managers; S: AI/ML Lead; C: Risk Analyst, ESG Lead; I: Steering Committee | 2025-06-27 | 2025-06-30 | 4 | 4 | 1.2 | Yes | User stories & pain points list | Fear of “black-box” AI; may require extra time to build trust
1.7 | Align with Technology & Data Management (CTO, IT) on High-Level Feasibility | R: Lead Data Engineer; A: CTO; S: Project Manager; C: AI/ML Lead, DevOps Engineer; I: Steering Committee | 2025-07-01 | 2025-07-03 | 3 | 3 | 1.2 | Yes | Preliminary tech feasibility notes | Integration constraints (legacy systems) may limit approaches
1.8 | Legal & Compliance Review of Data Usage (Alt Data, Privacy, Licensing) | R: Compliance Officer; A: Legal Head; S: Compliance Analyst; C: Data Engineer, Product Manager; I: Steering Committee | 2025-07-04 | 2025-07-06 | 3 | 3 | 1.2 | Yes | Data usage approval memos | If any data sources need additional legal review, timeline may slip
1.9 | Consolidate All Stakeholder Inputs into a “Stakeholder Alignment Report” | R: Product Manager; A: Sponsor; S: Project Manager; C: All SMEs; I: Steering Committee | 2025-07-07 | 2025-07-09 | 3 | 3 | 1.3–1.8 | Yes | “Stakeholder Alignment Report” | Conflicting priorities among stakeholders may need arbitration
1.1 | Steering Committee Sign-off on Stakeholder Alignment Report | R: Sponsor; A: Steering Committee Chair; S: Project Manager; C: Product Manager; I: All Stakeholders | 2025-07-10 | 2025-07-10 | 1 | 1 | 1.9 | Yes | Approval sign-off document | If sign-off delayed, all downstream tasks shift
2.1 | Create & Distribute Detailed Requirements Questionnaire to Each Stakeholder Group | R: Business Analyst; A: Product Manager; S: Project Manager; C: All SMEs; I: Steering Committee | 2025-07-11 | 2025-07-13 | 3 | 2 | 1.10 | Yes | List of questionnaire responses from all groups | Some SMEs may not complete on time; assumption that questionnaire captures top-level needs
2.2 | Conduct Deep-Dive Interview with Investment Leadership to Flesh Out Business Objectives | R: Business Analyst; A: CIOs; S: Product Manager; C: AI/ML Lead, Risk Analyst; I: Steering Committee | 2025-07-14 | 2025-07-18 | 5 | 5 | 2.1 | Yes | Updated user stories for investment decision support | May uncover conflicting objectives (e.g., short-term vs. long-term signals)
2.3 | Conduct Deep-Dive Interview with Risk Committee & CRO to Detail Risk Tolerances & Scenarios | R: Business Analyst; A: CRO; S: Risk Analyst; C: AI/ML Lead, Quant Researcher; I: Steering Committee | 2025-07-19 | 2025-07-23 | 5 | 5 | 2.1 | Yes | Detailed risk requirements (VaR freq, stress vectors, limits) | Regulatory changes mid-period could alter requirements
2.4 | Conduct Deep-Dive Interview with ESG Team to Specify ESG Metrics & Reporting Needs | R: Business Analyst; A: ESG Head; S: ESG Analyst; C: AI/ML Lead, Compliance; I: Steering Committee | 2025-07-24 | 2025-07-28 | 5 | 5 | 2.1 | Yes | ESG feature requirements (e.g., carbon, controversies) | ESG metric providers may have data lags; assume vendor can supply historical data
2.5 | Conduct Deep-Dive Interview with Front-line Investment Teams for Workflow Integration Needs | R: Business Analyst; A: Portfolio Managers; S: Product Manager; C: UI/UX Lead, Front-end Engineer; I: Steering Committee | 2025-07-29 | 2025-08-02 | 5 | 5 | 2.1 | Yes | Workflow integration requirements (dashboard, alerts) | Investment teams have different workflows; might need multiple dashboards
2.6 | Technical Constraints Workshop with IT (Data Warehouse, Security, Access Controls) | R: Business Analyst; A: CTO; S: Lead Data Engineer; C: DevOps Engineer, Security Officer; I: Steering Committee | 2025-08-03 | 2025-08-07 | 5 | 5 | 2.1 | Yes | Technical requirements doc (scalability, security, latency) | Legacy systems may limit data integration; assume enough bandwidth/compute
2.7 | Legal & Compliance Workshop on Data Privacy, Usage, Licensing | R: Business Analyst; A: Legal Head; S: Compliance Analyst; C: Data Engineer, Product Manager; I: Steering Committee | 2025-08-08 | 2025-08-12 | 5 | 5 | 2.1 | Yes | Compliance requirements doc (GDPR, ADGM/FSRA, vendor terms) | If new regulations emerge, may need rework
2.8 | Synthesize All Inputs into a “Combined Requirements Specification” Document | R: Business Analyst; A: Product Manager; S: Project Manager; C: All SMEs; I: Steering Committee | 2025-08-13 | 2025-08-15 | 3 | 3 | 2.2–2.7 | Yes | Finalized “Requirements Specification” (with user stories & acceptance criteria) | Assumes no major stakeholder changes after this point
3.1 | Draft Detailed Role Descriptions & Skill Requirements | R: Project Manager; A: Sponsor; S: Product Manager; C: HR Lead, CTO; I: Steering Committee | 2025-08-16 | 2025-08-18 | 3 | 3 | 2.8 | Yes | Role/Skill doc (data engineers, ML, quant, front-end, etc.) | Too many specialized skills required—may need external hires
3.2 | Identify Internal Candidates & Gaps Analysis for Each Role | R: HR/Resource Coordinator; A: Product Manager; S: Project Manager; C: Department Heads; I: Steering Committee | 2025-08-19 | 2025-08-21 | 3 | 3 | 3.1 | Yes | Gap analysis report (who exists vs. who needed) | Internal staff may be over-committed; need to reprioritize existing projects
3.3 | Post Job Reqs for New Hires / Engage Contractors for Specialized Roles | R: HR/Resource Coordinator; A: Project Manager; S: Product Manager; C: Procurement, Legal; I: Steering Committee | 2025-08-22 | 2025-08-25 | 4 | 4 | 3.2 | Yes | Published job postings & contractor RFP | Hiring delays; budget approvals; contractor selection process might drag
3.4 | Interview & Select Candidates for Data Engineers, ML Engineers, Quant Researchers | R: HR Lead; A: Product Manager; S: Team Leads (Data, ML, Quant); C: CTO, AI/ML Lead; I: Steering Committee | 2025-08-26 | 2025-08-29 | 4 | 4 | 3.3 | Yes | Hire decisions & offer letters | Candidate offers may be declined; need plan B candidates
3.5 | Onboard New Hires & Conduct Initial Orientation (Tech Stack, Standards, Projects) | R: HR/Resource Coordinator; A: Project Manager; S: Lead Data Engineer, ML Lead; C: DevOps Engineer; I: All Team Members | 2025-08-30 | 2025-08-30 | 1 | 1 | 3.4 | Yes | Completed onboarding checklist for each new hire | Overlapping onboarding tasks; need coordination with IT for accounts/access
3.6 | Assign Project Roles & Finalize RACI Matrix | R: Project Manager; A: Sponsor; S: Product Manager; C: All Team Leads; I: All Team Members | 2025-08-30 | 2025-08-31 | 2 | 2 | 3.5 | Yes | Published RACI matrix (who does what) | Role clarity issues if overlapping responsibilities
3.7 | Conduct “Team Kickoff & Alignment” Session (Process, Tools, Communication Channels) | R: Project Manager; A: Sponsor; S: Scrum Master; C: All Team Leads; I: All Team Members | 2025-09-01 | 2025-09-02 | 2 | 2 | 3.6 | Yes | Team kickoff slide deck & notes | Geographic/time-zone coordination if team is distributed
4.1 | Convene Architecture Working Group Kickoff | R: Lead Data Engineer; A: CTO; S: Project Manager; C: AI/ML Lead, DevOps Engineer, Security Officer; I: Steering Committee | 2025-09-03 | 2025-09-03 | 1 | 1 | 3.7 | Yes | Architecture WG charter and schedule | WG member availability; clear scope definitions required
4.2 | Gather Existing Infrastructure Inventory & Constraints | R: Lead Data Engineer; A: CTO; S: DevOps Engineer; C: IT Ops, Security; I: Architecture WG | 2025-09-04 | 2025-09-08 | 5 | 5 | 4.1 | Yes | Current infra inventory & constraint document | Incomplete inventory may delay decisions
4.3 | Define System Requirements (Non-Functional & Functional) | R: Lead Data Engineer, AI/ML Lead; A: CTO; S: Architecture WG; C: Security Officer, Risk Analyst; I: Steering Committee | 2025-09-09 | 2025-09-15 | 5 | 5 | 2.8,4.2 | Yes | Technical requirements spec (scalability, latency, security, compliance) | Requirements must align with stakeholder needs; potential scope creep
4.4 | Identify Candidate Vendor Solutions for Key Components | R: AI/ML Lead; A: CTO; S: Product Manager; C: Procurement, Data Engineer; I: Architecture WG | 2025-09-16 | 2025-09-22 | 5 | 5 | 4.3 | Yes | Shortlist of vendor solutions (e.g., AI platform, risk engine, data providers) | Vendor responsiveness; NDA and confidentiality requirements
4.5 | Conduct Build-vs-Buy Analysis for Each Major Component | R: AI/ML Lead, Lead Data Engineer; A: CTO; S: Product Manager; C: Risk Analyst, Compliance; I: Steering Committee | 2025-09-23 | 2025-09-29 | 5 | 5 | 4.4 | Yes | Detailed build-vs-buy matrix with TCO, timelines, risks | Accurate vendor cost data; internal build estimates may vary
4.6 | Finalize Target Technical Architecture Diagram | R: Lead Data Engineer; A: CTO; S: AI/ML Lead; C: DevOps Engineer, Security Officer; I: Steering Committee | 2025-09-30 | 2025-10-03 | 4 | 4 | 4.5 | Yes | High-fidelity architecture diagram (data, ML, app layers) | Alignment with compliance and security policies required
5.1 | Define Sprint Structure, Ceremonies, and Roles | R: Project Manager; A: Sponsor; S: Scrum Master; C: All Team Leads; I: Steering Committee | 2025-10-04 | 2025-10-06 | 3 | 3 | 4.6 | No | Sprint operating model document | Assumes team's agile literacy; need agile training if gaps
5.2 | Set Up Project Tracking Tools (Jira/Azure Boards, Confluence) | R: Project Manager; A: Sponsor; S: Scrum Master; C: IT Admin; I: All Team Members | 2025-10-07 | 2025-10-09 | 3 | 3 | 5.1 | No | Configured Jira boards, Confluence space | Licensing issues; access permissions setup delays
5.3 | Develop Risk & Issue Management Processes (Risk Register, Escalation Path) | R: Risk Analyst; A: CRO; S: Project Manager; C: Compliance, CTO; I: Steering Committee | 2025-10-10 | 2025-10-14 | 5 | 5 | 5.1 | No | Risk & Issue Management Handbook | Need alignment with enterprise risk governance
6.1 | Provision Cloud Resources (Dev Subscription, Storage, Compute) | R: DevOps/MLOps Engineer; A: CTO; S: Lead Data Engineer; C: Security Officer; I: Team | 2025-10-15 | 2025-10-17 | 3 | 3 | 4.6 | Yes | Dev environment with data lake, compute clusters, networking configured | Cloud subscription provisioning delays; network/security approvals
6.2 | Set Up CI/CD Pipeline for Data Pipelines (Airflow/ADF) | R: DevOps/MLOps Engineer; A: CTO; S: Lead Data Engineer; C: AI/ML Lead; I: Team | 2025-10-18 | 2025-10-22 | 5 | 5 | 6.1 | Yes | CI/CD workflow for ETL pipelines configured | Pipeline failures due to infra misconfig; credential management issues
6.3 | Set Up CI/CD Pipeline for ML Models (MLflow, Docker Registry) | R: DevOps/MLOps Engineer; A: CTO; S: AI/ML Lead; C: Lead Data Engineer; I: Team | 2025-10-23 | 2025-10-27 | 5 | 5 | 6.1 | Yes | Automated model build, test, and registry pipeline | MLflow version compatibility; Docker registry access
6.4 | Set Up CI/CD Pipeline for Application & API Deployment | R: DevOps/MLOps Engineer; A: CTO; S: Software Engineer; C: Security Officer; I: Team | 2025-10-28 | 2025-10-31 | 4 | 4 | 6.1 | Yes | CI/CD for API and frontend deployment configured | Container orchestration (Kubernetes) setup delays
7.1 | Obtain & Validate Twitter API Credentials and Rate Limits | R: Data Engineer; A: Lead Data Engineer; S: Product Manager; C: Compliance; I: Team | 2025-11-01 | 2025-11-02 | 2 | 2 | 6.2,6.3,6.4 | Yes | Valid Twitter API keys and documented rate limits | Twitter policy changes; credential approval delays
7.2 | Design Data Schema for Raw Twitter Data (Data Lake) | R: Lead Data Engineer; A: CTO; S: Data Engineer; C: AI/ML Lead; I: Team | 2025-11-03 | 2025-11-05 | 3 | 3 | 7.1 | Yes | Raw data schema design document (JSON/Parquet definitions) | Evolving data fields from Twitter; schema changes over time
7.3 | Implement Twitter Data Ingestion Script (Python) | R: Data Engineer; A: Lead Data Engineer; S: AI/ML Lead; C: DevOps Engineer; I: Team | 2025-11-06 | 2025-11-14 | 7 | 7 | 7.2 | Yes | Python ingestion script writing raw JSON to Data Lake | Rate limit errors; streaming failures
7.4 | Test & Validate Ingestion Logic (Dev) | R: Lead Data Engineer; A: Lead Data Engineer; S: Data Engineer; C: AI/ML Lead; I: Team | 2025-11-15 | 2025-11-18 | 4 | 4 | 7.3 | Yes | Test report with ingestion success, sample raw files in lake | Incomplete data capture; timestamp misalignment
7.5 | Deploy Ingestion to CI/CD and Schedule as CronJob | R: DevOps/MLOps Engineer; A: CTO; S: Data Engineer; C: Security Officer; I: Team | 2025-11-19 | 2025-11-22 | 4 | 4 | 7.4 | Yes | Scheduled ingestion job (daily at 1 AM) in production | CronJob failures; environment config errors
7.6 | Monitor & Alert Setup for Ingestion Failures | R: DevOps/MLOps Engineer; A: CTO; S: Data Engineer; C: Security Officer; I: Team | 2025-11-23 | 2025-11-24 | 2 | 2 | 7.5 | No | Alerts configured (e.g., Slack/email) for ingestion issues | False positives; monitoring configuration errors
8.1 | Design Sentiment Feature Schema (Daily Aggregates) | R: Lead Data Engineer; A: CTO; S: Data Engineer; C: AI/ML Lead; I: Team | 2025-11-25 | 2025-11-26 | 2 | 2 | 7.5 | Yes | Feature schema doc (avg sentiment, count, stddev, 3-day rolling) | Need sample data to validate schema; missing fields
8.2 | Implement Sentiment Feature Engineering Script (PySpark/Pandas) | R: Data Engineer; A: Lead Data Engineer; S: AI/ML Lead; C: DevOps Engineer; I: Team | 2025-11-27 | 2025-12-05 | 7 | 7 | 8.1 | Yes | Script that reads raw JSON, writes to curated.sentiment_features table | Data skew; transformation errors; compute resource limits
8.3 | Test & Validate Sentiment Features (Dev) | R: Lead Data Engineer; A: Lead Data Engineer; S: Data Engineer; C: AI/ML Lead; I: Team | 2025-12-06 | 2025-12-09 | 4 | 4 | 8.2 | Yes | Validation report and sample feature rows | Feature values out of expected range; missing data
8.4 | Deploy Sentiment Feature Job to CI/CD & Schedule (2 AM Daily) | R: DevOps/MLOps Engineer; A: CTO; S: Data Engineer; C: Security Officer; I: Team | 2025-12-10 | 2025-12-11 | 2 | 2 | 8.3 | Yes | Scheduled sentiment feature job in production | Job failures; configuration drift between dev and prod
9.1 | Define Initial Optimization Formulation (Objective, Constraints) | R: AI/ML Lead, Quantitative Researcher; A: AI/ML Lead; S: Product Manager; C: Risk Analyst, CTO; I: Team | 2025-12-12 | 2025-12-13 | 2 | 2 | 8.4 | Yes | Documented optimization problem (v0) | Simplified risk may not be acceptable; need quick stakeholder check
9.2 | Implement Optimization Script (cvxpy) Using Sentiment Features | R: Software Engineer; A: AI/ML Lead; S: Quantitative Researcher; C: Lead Data Engineer; I: Team | 2025-12-14 | 2025-12-22 | 7 | 7 | 9.1 | Yes | optimize.py writing optimized_weights_v0 table | Solver convergence issues; missing covariance matrix for basic risk
9.3 | Test & Validate Optimizer Logic (Dev) | R: Lead Data Engineer; A: AI/ML Lead; S: Software Engineer; C: Quant Researcher; I: Team | 2025-12-23 | 2026-01-02 | 7 | 7 | 9.2 | Yes | Optimizer test report with sample weights | Unexpected weight allocations; missing data alignments
9.4 | Deploy Optimization Service to CI/CD & Schedule (4 AM Daily) | R: DevOps/MLOps Engineer; A: CTO; S: Software Engineer; C: Security Officer; I: Team | 2026-01-03 | 2026-01-05 | 3 | 3 | 9.3 | Yes | Production optimizer CronJob & API endpoint deployment | API security; production environment config differences
9.5 | Design Dashboard Wireframe & API Specifications | R: Front-end Engineer; A: Product Manager; S: UI/UX Lead; C: AI/ML Lead, Risk Analyst; I: Stakeholders | 2026-01-06 | 2026-01-07 | 2 | 2 | 9.4 | Yes | Wireframe diagrams & API spec document | Stakeholder availability for review; potential revisions required
9.6 | Implement Front-end Code for Weights & Risk Panel (Dashboard v0) | R: Front-end Engineer; A: Product Manager; S: UI/UX Lead; C: Software Engineer, Risk Analyst; I: Team | 2026-01-08 | 2026-01-14 | 7 | 7 | 9.5 | Yes | Dashboard v0 codebase (table, chart, risk panel) | CORS issues; API response changes; styling inconsistencies
9.7 | Test & Validate Dashboard v0 in Dev | R: QA Analyst; A: Product Manager; S: Front-end Engineer; C: Risk Analyst, AI/ML Lead; I: Team | 2026-01-15 | 2026-01-18 | 4 | 4 | 9.6 | Yes | Dashboard v0 test report; bug list | UI bugs; data mismatches; cross-browser issues
9.8 | Deploy Dashboard v0 to Staging with Authentication | R: DevOps/MLOps Engineer; A: CTO; S: Front-end Engineer; C: Security Officer; I: Team | 2026-01-19 | 2026-01-20 | 2 | 2 | 9.7 | Yes | Staging dashboard URL with Azure AD auth | Authentication misconfiguration; staging environment instability
9.9 | Collect Feedback & Iterate Dashboard v0 | R: Product Manager; A: Sponsor; S: Front-end Engineer; C: Portfolio Managers, Risk Analyst; I: Steering Committee | 2026-01-21 | 2026-01-23 | 3 | 3 | 9.8 | No | Feedback log & updated tasks for next iteration | Users may request major changes; iteration scope creep
10.1 | Gather Historical Return Data & Ticker Mapping | R: Data Engineer; A: Lead Data Engineer; S: Quantitative Researcher; C: Risk Analyst; I: Team | 2026-01-24 | 2026-01-26 | 3 | 3 | 9.9 | Yes | Cleaned historical returns table & ticker list | Missing data for delisted tickers; data licensing constraints
10.2 | Implement Covariance Matrix Calculation Script | R: Quantitative Researcher; A: Risk Analyst; S: Software Engineer; C: Data Engineer; I: Team | 2026-01-27 | 2026-02-02 | 5 | 5 | 10.1 | Yes | Python script computing covariance matrix, portfolio variance | High memory usage for large universes; inaccurate covariance if insufficient data
10.3 | Implement VaR, CVaR & Stress Test Calculations | R: Risk Analyst; A: CRO; S: Software Engineer; C: Quantitative Researcher; I: Team | 2026-02-03 | 2026-02-09 | 5 | 5 | 10.2 | Yes | Extended script that outputs VaR_95, CVaR_95, stress losses | Normality assumption may not hold; scenario correlation assumptions
10.4 | Test & Validate Risk Engine in Dev | R: QA Analyst; A: Risk Analyst; S: Software Engineer; C: Quantitative Researcher; I: Team | 2026-02-10 | 2026-02-13 | 4 | 4 | 10.3 | Yes | Risk engine test report with accuracy validation | Discrepancies in stress test outcomes; rounding errors
10.5 | Deploy Risk Engine CronJob & Expose Detailed Risk API | R: DevOps/MLOps Engineer; A: CTO; S: Software Engineer; C: Security Officer; I: Team | 2026-02-14 | 2026-02-16 | 3 | 3 | 10.4 | Yes | Daily risk CronJob & /api/v1/portfolio-risk-detailed endpoint | API security; job scheduling conflicts
10.6 | Validate Detailed Risk API & Monitor Alerts | R: QA Analyst; A: Risk Analyst; S: Software Engineer; C: DevOps Engineer; I: Team | 2026-02-17 | 2026-02-18 | 2 | 2 | 10.5 | No | API validation report & alert configurations | Delayed error detection; misconfigured alert thresholds
11.1 | Acquire & Validate Glassdoor Data Subscription | R: Product Manager; A: Sponsor; S: Data Engineer; C: Legal, Procurement; I: Team | 2026-02-19 | 2026-02-21 | 3 | 3 | 10.6 | Yes | Subscription agreement & credentials | Vendor contract negotiations; data licensing constraints
11.2 | Design Glassdoor Raw Data Schema (Data Lake) | R: Lead Data Engineer; A: CTO; S: Data Engineer; C: AI/ML Lead; I: Team | 2026-02-22 | 2026-02-24 | 3 | 3 | 11.1 | Yes | Raw data schema doc (JSON/Parquet for Glassdoor reviews) | Schema changes if vendor updates data fields
11.3 | Implement Glassdoor Ingestion Script | R: Data Engineer; A: Lead Data Engineer; S: AI/ML Lead; C: Compliance; I: Team | 2026-02-25 | 2026-03-05 | 7 | 7 | 11.2 | Yes | Ingestion script writing raw data to Data Lake | API rate limits; data inconsistencies; compliance checks
11.4 | Test & Validate Glassdoor Ingestion (Dev) | R: QA Analyst; A: Lead Data Engineer; S: Data Engineer; C: AI/ML Lead; I: Team | 2026-03-06 | 2026-03-09 | 4 | 4 | 11.3 | Yes | Ingestion test report & sample raw files | Partial data fetch; inconsistent data formats
11.5 | Deploy Glassdoor Ingestion CronJob & Configure Alerts | R: DevOps/MLOps Engineer; A: CTO; S: Data Engineer; C: Security Officer; I: Team | 2026-03-10 | 2026-03-11 | 2 | 2 | 11.4 | Yes | Daily Glassdoor ingestion job & monitoring | Job failures; alert noise if data variance
11.6 | Design Culture Feature Schema (Aggregated Metrics) | R: Lead Data Engineer; A: CTO; S: Data Engineer; C: AI/ML Lead; I: Team | 2026-03-12 | 2026-03-14 | 3 | 3 | 11.5 | Yes | Schema doc for curated.company_culture_features | Data sparsity for some tickers; need fallback defaults
11.7 | Implement Culture Feature Engineering Script | R: Data Engineer; A: Lead Data Engineer; S: AI/ML Lead; C: DevOps Engineer; I: Team | 2026-03-15 | 2026-03-23 | 7 | 7 | 11.6 | Yes | Script writing curated.company_culture_features table | Incorrect aggregations; missing data periods
11.8 | Test & Validate Culture Features (Dev) | R: QA Analyst; A: Lead Data Engineer; S: Data Engineer; C: AI/ML Lead; I: Team | 2026-03-24 | 2026-03-27 | 4 | 4 | 11.7 | Yes | Culture feature test report & sample rows | Feature anomalies; schema mismatches
11.9 | Deploy Culture Feature Job to CI/CD & Schedule (2 AM Daily) | R: DevOps/MLOps Engineer; A: CTO; S: Data Engineer; C: Security Officer; I: Team | 2026-03-28 | 2026-03-29 | 2 | 2 | 11.8 | Yes | Scheduled culture feature job | Cron job config drift; resource contention
11.1 | Design Combined Feature Schema (Merge Sentiment & Culture) | R: Lead Data Engineer; A: CTO; S: Data Engineer; C: AI/ML Lead; I: Team | 2026-03-30 | 2026-04-01 | 3 | 3 | 11.9,8.4 | Yes | Schema doc for curated.combined_features | Join key mismatches; data latency differences
11.11 | Implement Combined Feature Engineering Script | R: Data Engineer; A: Lead Data Engineer; S: AI/ML Lead; C: DevOps Engineer; I: Team | 2026-04-02 | 2026-04-10 | 7 | 7 | 11.10 | Yes | Script writing curated.combined_features_v0 | Schema changes; missing sentiment or culture rows
11.12 | Test & Validate Combined Features (Dev) | R: QA Analyst; A: Lead Data Engineer; S: Data Engineer; C: AI/ML Lead; I: Team | 2026-04-11 | 2026-04-14 | 4 | 4 | 11.11 | Yes | Combined feature test report & sample rows | Inconsistent feature values; query performance issues
11.13 | Deploy Combined Feature Job to CI/CD & Schedule (3 AM Daily) | R: DevOps/MLOps Engineer; A: CTO; S: Data Engineer; C: Security Officer; I: Team | 2026-04-15 | 2026-04-16 | 2 | 2 | 11.12 | Yes | Scheduled combined feature job | Cron timing; environment differences
12.1 | Prepare Training Dataset Pipeline for v1 Model | R: Data Engineer; A: Lead Data Engineer; S: AI/ML Lead; C: Quantitative Researcher; I: Team | 2026-04-17 | 2026-04-19 | 3 | 3 | 11.13 | Yes | Jupyter notebook or script to join combined_features_v0 with historical returns | Data alignment; missing labels for target variable
12.2 | Develop & Train XGBoost Model Using Combined Features | R: AI/ML Lead; A: AI/ML Lead; S: Quantitative Researcher; C: Data Engineer; I: Team | 2026-04-20 | 2026-04-26 | 7 | 7 | 12.1 | Yes | Trained model artifact logged in MLflow (sentiment_culture_v1) | Overfitting; feature importance mismatch
12.3 | Evaluate & Validate v1 Model Performance | R: AI/ML Lead; A: Risk Analyst; S: Quantitative Researcher; C: Software Engineer; I: Team | 2026-04-27 | 2026-04-30 | 4 | 4 | 12.2 | Yes | Model evaluation report (metrics, feature importance) | Model underperformance vs. v0; additional feature engineering required
12.4 | Log Model v1 to MLflow & Tag for Deployment | R: AI/ML Lead; A: AI/ML Lead; S: Software Engineer; C: DevOps Engineer; I: Team | 2026-05-01 | 2026-05-02 | 2 | 2 | 12.3 | Yes | MLflow model entry with tags (production-ready) | MLflow version issues; artifact storage misconfig
12.5 | Update optimize.py to Use Combined Model v1 Outputs | R: Software Engineer; A: AI/ML Lead; S: Quantitative Researcher; C: Data Engineer; I: Team | 2026-05-03 | 2026-05-07 | 5 | 5 | 12.4 | Yes | optimize_v1.py script writing optimized_weights_v1 table | Model artifact path changes; new risk constraints
12.6 | Test & Validate Optimizer v1 in Dev | R: Quantitative Researcher; A: AI/ML Lead; S: Software Engineer; C: Risk Analyst; I: Team | 2026-05-08 | 2026-05-12 | 5 | 5 | 12.5 | Yes | Optimizer v1 test report with sample weights and risk compliance | Weight anomalies; model input mismatches
12.7 | Deploy Optimizer v1 CronJob & Expose /api/v1/optimized-weights-v1 | R: DevOps/MLOps Engineer; A: CTO; S: Software Engineer; C: Security Officer; I: Team | 2026-05-13 | 2026-05-15 | 3 | 3 | 12.6 | Yes | Scheduled optimizer v1 job and new API endpoint | Production config drift; API conflicts
12.8 | Validate Optimizer v1 API & Monitor Job | R: QA Analyst; A: AI/ML Lead; S: Software Engineer; C: DevOps Engineer; I: Team | 2026-05-16 | 2026-05-17 | 2 | 2 | 12.7 | No | v1 API validation report & job monitoring setup | Latency spikes; job failures unreported
13.1 | Provision Pilot Historical Data Environment | R: Lead Data Engineer; A: Product Manager; S: DevOps/MLOps Engineer; C: Quantitative Researcher; I: Team | 2026-05-18 | 2026-05-19 | 2 | 2 | 12.8 | Yes | Pilot environment (dev clone) with historical data access | Storage costs; data completeness; environment parity
13.2 | Backfill Alternative & Combined Features for Historical Period | R: Data Engineer; A: Lead Data Engineer; S: AI/ML Lead; C: Quantitative Researcher; I: Team | 2026-05-20 | 2026-05-27 | 6 | 6 | 13.1 | Yes | Historical feature tables populated (last 2 years) | Data retention policies; vendor data availability for past periods
13.3 | Run Optimizer v1 Historically & Compare Portfolio Metrics | R: Quantitative Researcher; A: AI/ML Lead; S: Software Engineer; C: Risk Analyst; I: Team | 2026-05-28 | 2026-06-02 | 6 | 6 | 13.2 | Yes | Backtest results report (performance vs baseline) | Computational intensity; alignment with historical risk limits
13.4 | Generate Pilot Performance & Validation Report | R: Product Manager; A: Sponsor; S: AI/ML Lead; C: Quantitative Researcher, Risk Analyst; I: Steering Committee | 2026-06-03 | 2026-06-05 | 3 | 3 | 13.3 | Yes | Pilot report with key metrics and recommendations | Report accuracy; stakeholder alignment on metrics
13.5 | Provision Pilot Shadow Live Environment for Selected Portfolios | R: DevOps/MLOps Engineer; A: CTO; S: Lead Data Engineer; C: Compliance, Risk Analyst; I: Team | 2026-06-06 | 2026-06-08 | 3 | 3 | 13.4 | Yes | Pilot shadow environment running live data feeds | Data security in shadow; user access issues
14.1 | Distribute Pilot Access to Selected Portfolio Managers & Risk Team | R: Product Manager; A: Sponsor; S: Scrum Master; C: Team Leads; I: Pilot Users | 2026-06-09 | 2026-06-10 | 2 | 2 | 13.5 | No | Access credentials and user instructions | User onboarding delays; access troubleshooting
14.2 | Collect Pilot User Feedback Over 2 Weeks | R: Product Manager; A: Sponsor; S: Scrum Master; C: Team Leads; I: Pilot Users | 2026-06-11 | 2026-06-24 | 10 | 10 | 14.1 | No | Consolidated feedback log | Low user engagement; feedback not representative
14.3 | Analyze Feedback & Create Issue Backlog for Refinements | R: Business Analyst; A: Product Manager; S: Scrum Master; C: Team Leads; I: Steering Committee | 2026-06-25 | 2026-06-26 | 2 | 2 | 14.2 | No | Issue backlog with priority and estimates | Conflicting feedback; prioritization challenges
15.1 | Provision Production Environment Resources | R: DevOps/MLOps Engineer; A: CTO; S: Lead Data Engineer; C: Security Officer; I: Team | 2026-06-27 | 2026-06-29 | 3 | 3 | 14.3 | Yes | Production cloud resources (data lake, compute, networking) | Approval delays; quota limits
15.2 | Migrate CI/CD Pipelines from Dev to Production | R: DevOps/MLOps Engineer; A: CTO; S: Software Engineer; C: Security Officer; I: Team | 2026-06-30 | 2026-07-02 | 3 | 3 | 15.1 | Yes | CI/CD pipelines running in production context | Credential mismatches; environment differences
15.3 | Conduct Security Audit & Penetration Test on Production | R: Security Officer; A: CTO; S: DevOps/MLOps Engineer; C: External Auditor; I: Team | 2026-07-03 | 2026-07-07 | 5 | 5 | 15.2 | Yes | Security audit report with remediation plan | Findings requiring changes; potential delays
15.4 | Create Final Cutover Plan & Schedule | R: Project Manager; A: Sponsor; S: DevOps/MLOps Engineer; C: All Team Leads; I: Steering Committee | 2026-07-08 | 2026-07-09 | 2 | 2 | 15.3 | Yes | Approved cutover checklist & timeline | Stakeholder sign-off delays; downtime coordination
16.1 | Develop User Training Materials (Slides, Videos, Tutorials) | R: Product Manager; A: Sponsor; S: Front-end Engineer, Lead Data Engineer; C: AI/ML Lead, Risk Analyst; I: All Users | 2026-07-10 | 2026-07-14 | 5 | 5 | 15.4 | Yes | Training deck, tutorial videos, quick reference guides | Incomplete features requiring updates; translation/localization needs
16.2 | Conduct Training Sessions for Portfolio Managers, Risk, IT Support | R: Product Manager; A: Sponsor; S: Lead Data Engineer, Front-end Engineer; C: AI/ML Lead, Risk Analyst; I: All Users | 2026-07-15 | 2026-07-17 | 3 | 3 | 16.1 | Yes | Training sign-off sheets & attendance logs | User availability; training skill gaps
16.3 | Publish Final Documentation (User Guide, Tech Spec, Runbooks) | R: Lead Data Engineer; A: CTO; S: Product Manager; C: AI/ML Lead, Risk Analyst; I: All Users | 2026-07-18 | 2026-07-20 | 3 | 3 | 16.2 | Yes | Consolidated documentation portal (Confluence/SharePoint) | Outdated docs if last-minute changes occur; access permissions
17.1 | Identify Legacy Processes & Systems to Retire | R: Project Manager; A: Sponsor; S: IT Operations Lead; C: All Team Leads; I: All Users | 2026-07-21 | 2026-07-22 | 2 | 2 | 16.3 | Yes | Legacy inventory & retirement plan | Unknown dependencies on legacy systems; user resistance
17.2 | Execute Data Migration from Legacy to New System (if needed) | R: Data Engineer; A: Lead Data Engineer; S: IT Ops Lead; C: Compliance, Risk Analyst; I: Team | 2026-07-23 | 2026-07-26 | 4 | 4 | 17.1 | Yes | Data migration scripts & migrated data verification report | Data loss risk; mapping errors; downtime required
17.3 | Validate New System Covers All Legacy Requirements | R: QA Analyst; A: Product Manager; S: Software Engineer; C: IT Ops Lead; I: Team | 2026-07-27 | 2026-07-29 | 3 | 3 | 17.2 | Yes | Validation report confirming feature parity | Missed edge-case legacy workflows; inadequate test coverage
17.4 | Deactivate Legacy Jobs & Monitor New System Stability | R: IT Operations Lead; A: Project Manager; S: DevOps/MLOps Engineer; C: QA Analyst; I: Team | 2026-07-30 | 2026-07-31 | 2 | 2 | 17.3 | Yes | Legacy decommission logs & new system monitoring dashboards | Critical failure in new system; rollback plan needed
17.5 | Document Legacy Decommission Report & Lessons Learned | R: Project Manager; A: Sponsor; S: Business Analyst; C: All Team Leads; I: Organization | 2026-08-01 | 2026-08-02 | 2 | 2 | 17.4 | Yes | Final Decommission & Lessons Learned Report | Incomplete knowledge capture; stakeholder buy-in on lessons